## RP - Detail Progress
විහාරස්ථාන සංවර්ධනය -2025
Physical and Financial Progress as at 30.06.2025
District:-Gampaha
Divisional Secreteriat- |  |  | Aththanagalla
No. | ග්‍රාම නිලධාරි වසම | ව්‍යාපෘති අංකය | Name of the Project | Approved Amount (Rs) | Project Estimated Cost | contract Amount | ** Physical Progress (No. of Projects) | [10 empty] | Expenditure (Rs. ) | Bills in hand (Rs.) | No. of Beneficiaries
[7 empty] | A | B |  |  |  | C | D | E | F | G
[8 empty] | Estimates Approved & Bid Documents Approved (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4) |  |  |  |  | Construction | Goods & Services
| කිත්තම්මහර | MBRCA/RBT/2025/GAM/03 | කිත්තම්මහර දස්සනාරාමයේ ආවාසගෙය අලුත්වැඩියා කිරීම | 500000 | 500000 |  |  | 1
| කඹුරාගල්ල | MBRCA/RBT/2025/GAM/04 | කඹුරාගල්ල ශ්‍රී බෝධිරුක්ඛාරාමයේ සංඝාවාසයේ කාමරයක් ටයිල් කිරීම හා සිවිලිම සකස කර ගැනීම | 500000 | 500000 |  |  | 1
| උඩුගොඩ | MBRCA/RBT/2025/GAM/05 | උඩුගොඩ ශ්‍රී තපෝදාරාමයේ බණ මඩුවේ වහලය පිළිසකර කර ගැනීම | 500000 | 500000 |  |  | 1
Sub total |  |  |  | 1500000 | 1500000 |  |  | 3
Admin cost
Total
50

## RP Sector (hidden)
Piriven Development Programme - 2024
Physical and Financial Progress as at 28th October 2024
District:-Gampaha
| Divisional Secreteriat- | Aththanagalla | [12 empty] | Sector Progress
SN | Sector | No of Project | Project Estimated Cost | contract Amount | Physical Progress (c) | [10 empty] | Expenditure (Rs. ) | Bills in hand (Rs.) | No. of Beneficiaries
[5 empty] | A | B |  |  |  | C | D | E | F | G
[6 empty] | B -1 | B -2 | B-3 | B-4
[5 empty] | Estimates are being/ to be prepared | Estimate Approved & Bid Document Approved | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 41-60% | 61-80% | 81-99% | Construction | Goods & Services
1 | PP - Previous Projects Continuation
2 | TD -Tourism development
3 | DWS - drinking Water supply
4 | EL-Electricity
5 | RA-Rural Access
6 | MD-Market Development such as Kadamandi/Weekly Fair/Sales Centers
7 | E&H-Education & Health
8 | P&L-Play Ground & Library
9 | MI-Minor Irigation
10 | AD-Agricultural Development
11 | CD-Community Development
12 | R&C-Relegious & Cultural Development | 4 | 1500000 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642669.93 | 0
13 | CP-Community Protection
14 | EPF-Emprowering of Poor Families
15 | ED- Enterpreneurship Development
16 | DM-Disaster Management
17 | RA- Rural Economy
18 | OD-Other Development
Sub Total |  | 4 | 1500000 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642669.93 | 0
Admin cost | [16 empty] | 0
Total |  | 4 | 1500000 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642669.93 | 0

## RP Authority (hidden)
පිරිවෙන් සංවර්ධනය
Piriven Development Programme - 2024
Physical and Financial Progress as at at 28th October 2024
District:-Gampaha
| Divisional Secreteriat- Aththanagalla | [13 empty] | Authority Progress
SN | Authority | No of Project | Approved Amount (Rs) | Project Estimated Cost | contract Amount | Physical Progress (c) | [10 empty] | Total Expenditure (Rs.) | Bill in hands (Rs) | No of Beneficiaries | Remarks
[6 empty] | A | B |  |  |  | C | D | E | F | G
[7 empty] | B -1 | B -2 | B-3 | B-4
[6 empty] | Estimates are being/ to be prepared | Estimate Approved & Bid Document Approved | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 41-60% | 61-80% | 81-99% | Construction | Goods & Services
1 | Divisional Secretariat, Aththanagalla
2 | Urban Council, ……
3 | Pradeshiya Sabha, Aththanagalla
4 | Zonal Education Director,………
5 | Divisional Engineer ,………………
Sub Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Admin cost
Total

## RP - Detail Progress (2) (hidden)
පිරිවෙන් සංවර්ධනය
Piriven Development Programme - 2024 Programme - 2024
Physical and Financial Progress as at 09th August 2024
District:-Gampaha
Divisional Secreteriat- | [7 empty] | Aththanagalla
No. | ග්‍රාම නිලධාරි වසම | Project No | [5 empty] | Name of the Project | Approved Amount (Rs)
|  | Division | Programme | Authority | Sector | No | Year
1 | 329ඒ, හිරිපිටිය දකුණ | ATT | TEM | 16 | 122 | 1 | 2024 | ශ්‍රී ප්‍රඥාසාර මූලික පිරිවෙනෙහි පිරිවෙන් ශාලාව ප්‍රතිසංස්කරණය කිරීම | 165000
2 | 370 පරණගම | ATT | TEM | 16 | 122 | 2 | 2024 | බප/ගම්/ ශ්‍රී විද්‍යාසාර මූලික පිරිවෙනෙහි සනීපාරක්ෂක පහසුකම් සංවර්ධනය කිරීම | 150000
3 | 324 බෙම්මුල්ල | ATT | TEM | 16 | 122 | 3 | 2024 | ශ්‍රී වර්ධන මූලික පිරිවෙනෙහි සනීපාරක්ෂක පහසුකම් | 500000
4 | 353බී, වළලියද්ද | ATT | TEM | 16 | 122 | 4 | 2024 | බප/ගම්/ සිරි සුමංගල විද්‍යායතන පිරිවෙනෙහි සනීපාරක්ෂක පහසුකම් සංවර්ධනය කිරීම | 500000

## ප්‍රගතිය- ගිණුම් අංශය (hidden)
ඇමුණූම 01
පිරිවෙන් ගොඩනැගිලි අලුත්වැඩියා කිරීමේ වැඩසටහන 2024
2024.08.20 දිනට ප්‍රගතිය
දිස්ත්‍රික්කය - ගම්පහ
ප්‍රාදේශීය ලේකම් කොට්ඨාසය - අත්තනගල්ල
Divisional Secreteriat- | [6 empty] | Aththanagalla
අනු අංකය | ව්‍යාපෘතියේ අංකය | [5 empty] | ව්‍යාපෘතියේ නම | ඇස්තමේන්තුගත මුදල රු. | මූල්‍ය ප්‍රගතිය |  |  | භෞතික ප්‍රගතිය
[9 empty] | අනුමත මුදල (රු.) | නිදහස් කළ මුදල (රු.) | වාර් තා කෙරෙන මාසයේ අවසාන දිනට මුළු වියදම රු. | වැඩ ආරම්භ කර ඇත. ප්‍රගතිය 0 - 25% | වැඩ කෙරීගෙන යයි. 25% - 50% | වැඩ අවසන්. ප්‍රගතිය 50% - 95% | ගෙවීම්කර ඇත. ප්‍රගතිය 95% - 100% | වෙනත්
1 | ATT | TEM | 16 | 122 | 1 | 2024 | ශ්‍රී ප්‍රඥාසාර මූලික පිරිවෙනෙහි පිරිවෙන් ශාලාව ප්‍රතිසංස්කරණය කිරීම | 165000 | 165000 |  | 0 |  |  | √
2 | ATT | TEM | 16 | 122 | 2 | 2024 | බප/ගම්/ ශ්‍රී විද්‍යාසාර මූලික පිරිවෙනෙහි සනීපාරක්ෂක පහසුකම් සංවර්ධනය කිරීම | 150000 | 150000 |  | 0 |  | √
3 | ATT | TEM | 16 | 122 | 3 | 2024 | ශ්‍රී වර්ධන මූලික පිරිවෙනෙහි සනීපාරක්ෂක පහසුකම් | 500000 | 500000 |  | 0 |  |  | √
4 | ATT | TEM | 16 | 122 | 4 | 2024 | බප/ගම්/ සිරි සුමංගල විද්‍යායතන පිරිවෙනෙහි සනීපාරක්ෂක පහසුකම් සංවර්ධනය කිරීම | 500000 | 500000 |  | 0 |  | √
Sub Total | [7 empty] | 1315000 | 1315000 |  | 0
සකස් කළේ - | [8 empty] | පරීක්ෂා කළේ - | [5 empty] | අනුමත කළේ -

## ප්‍රාලේ (hidden)
Decentralized Capital Budget Programme - 2019 - Gampaha District
Physical and Financial Progress of the 2019.06.22
Divisional Secretariat Division (a) | [8 empty] | Name: Ja Ela | [16 empty] | Annexure/DCB/02
[9 empty] | No: | [16 empty] | Detail Progress
SN | Project No | [6 empty] | Name of MP | Name of Project | G.N. Division (b) |  | Type of Project (Construction / Goods & Services) | Sector | Allocation - Value of the Project (Rs.) | Total Estimate Cost (Rs.) |  | Contract Amount (Rs) | Total Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
[20 empty] | A | B |  |  |  | C | D | E | F | G
| Division | MP No | Programme | Authority | Sector | No | Year |  |  | Name | No |  |  |  | With VAT | Without VAT |  |  |  |  | B -1 | B -2 | B-3 | B-4
[20 empty] | 0-5% | Estimate Approved & Bid Document Prepared | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 40-60% | 61-80% | 81-99% | 100%
1 | JAELA | 9 | DCB | 18 | 142 | 1 | 2019 | Ajith Mannapperuma | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ස්වයං රැකියා පුහුණු පාඨමාලා පැවැත්වීම. |  |  | Training Programs |  | 200000 | [5 empty] | 1
2 | JAELA | 18 | DCB | 18 | 121 | 2 | 2019 | Vijitha Herath | කළඑලිය ශාන්ත ජුවකීනු දේවස්ථාන දහම් පාසලේ ගොඩනැගිල්ල ඉදිකිරීම. |  |  | Construction |  | 200000 | 200000 | [13 empty] | 1
3 | JAELA | 18 | DCB | 18 | 142 | 3 | 2019 | Vijitha Herath | පසුව නම් කරනු ලබන ස්ථාන වල ස්වයං රැකියා පුහුණු වැඩසටහන් පැවැත්වීම. |  |  | Training Programs |  | 100000 | [5 empty] | 1
4 | JAELA | 18 | DCB | 18 | 516 | 4 | 2019 | Vijitha Herath | පසුව නම් කරනු ලබන පෙර පාසල් සඳහා උපකරණ ලබා දීම. |  |  | Goods & Services) |  | 50000 | [7 empty] | 1
5 | JAELA | 18 | DCB | 18 | 152 | 5 | 2019 | Vijitha Herath | පසුව නම් කරනු ලබන සංස්කෘතික සංගම් සඳහා උපකරණ ලබා දීම. |  |  | Goods & Services) |  | 100000 | [7 empty] | 1
6 | JAELA | 15 | DCB | 18 | 152 | 6 | 2019 | Sisira Jayakodi | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංච් සමිති සඳහා උපකරණ ලබා දීම. |  |  | Goods & Services) |  | 300000 | #REF! | [13 empty] | 1
7 | JAELA | 8 | DCB | 18 | 152 | 7 | 2019 | Nimal Lansa | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංච් නම් කරනු ලබන සමිති සමාගම් සඳහා ඇඳි නැති ප්ලාස්ටික් පුටු ලබා දීම. |  |  | Goods & Services) |  | 150000 | #REF! | [13 empty] | 1
8 | JAELA | 9 | DCB | 18 | 517 | 8 | 2019 | Ajith Mannapperuma | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ තෝරාගත් පෙර පාසල් ගුරු මහත්මීන් සඳහා පුහුණු වැඩමුළු පැවැත්වීම. |  |  | Training Programs |  | 100000 | [5 empty] | 1
9 | JAELA | 18 | DCB | 18 | 142 | 9 | 2019 | Vijitha Herath | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ තරුණයින් සඳහා බරවාහන පුහුණුව හා ලයිසන් ලබා දීම. |  |  | Training Programs |  | 100000 | [7 empty] | 1
10 | JAELA | 8 | DCB | 18 | 152 | 10 | 2019 | Nimal Lansa | ප්‍රාදේශීය ලේකම් කාර්යාලයේ ලියාපදිංචි ජා ඇල නිවන්දම සුහද සුභ සාධක සමිතිය සඳහා ෆොටෝකොපි යන්ත්‍රයක් සහ A/3 EBSOMI 1800 කලර් ෆොටෝකොපි ප්‍රින්ටරයක් ලබා දීම. |  |  | Goods & Services) |  | 300000 | [5 empty] | 1
11 | JAELA | 13 | DCB | 18 | 152 | 9 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංචි සමිති සඳහා රෙදි හට් ලබා දීම.(කැනපි හට්) |  |  | Goods & Services) |  | 500000 | [5 empty] | 1
12 | JAELA | 13 | DCB | 18 | 152 | 10 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංචි සමිති සඳහා කැනපි හට් ලබා දීම.(ෆුල් හට්) |  |  | Goods & Services) |  | 500000 | [5 empty] | 1
13 | JAELA | 13 | DCB | 18 | 152 | 11 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංචි සමිති සඳහා ප්ලාස්ටික් පුටු ලබා දීම. |  |  | Goods & Services) |  | 200000 | [5 empty] | 1
14 | JAELA | 13 | DCB | 18 | 173 | 1 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංච් ක්‍රීඩා සමිති හා සුභ සාධක සමිති සඳහා ක්‍රීඩා භාණ්ඩ ලබා දීම. |  |  | Goods & Services) |  | 500000 | [5 empty] | 1
15 | JAELA | 13 | DCB | 18 | 515 | 1 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියාපදිංචි පෙර පාසල් සංවර්ධනය කිරීම. |  |  | Construction |  | 240000 | [5 empty] | 1
16 | JAELA | 13 | DCB | 18 | 122 | 1 | 2019 |  | යක්කඩුව ශ්‍රී සද්ධර්මායෝද විහාරස්ථානයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 200000 | [5 empty] | 1
17 | JAELA | 13 | DCB | 18 | 122 | 2 | 2019 |  | ඒකල කුරුඳුවත්ත ශ්‍රී විමල කීර්ති පුෂ්පාරාමයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 200000 | [5 empty] | 1
18 | JAELA | 13 | DCB | 18 | 122 | 3 | 2019 |  | වල්පොල ශ්‍රී සුදත්තාරාමයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
19 | JAELA | 13 | DCB | 18 | 122 | 4 | 2019 |  | ඒකල ශ්‍රී අභිනවාරාමයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
20 | JAELA | 13 | DCB | 18 | 122 | 5 | 2019 |  | නිවන්දම ශ්‍රී දීපදුත්තාරාමයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
21 | JAELA | 13 | DCB | 18 | 122 | 6 | 2019 |  | ඒකල කුරුඳුවත්ත ශ්‍රීපාලි විහාරස්ථානයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
22 | JAELA | 13 | DCB | 18 | 122 | 7 | 2019 |  | පොල්පිටිමූකලාන ශ්‍රී වජිරාරාමයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 200000 | [5 empty] | 1
23 | JAELA | 13 | DCB | 18 | 122 | 8 | 2019 |  | දඹුව ශ්‍රී බෝධිරුක්ඛාරාමයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
24 | JAELA | 13 | DCB | 18 | 122 | 9 | 2019 |  | ආනියාකන්ද ශ්‍රි රාහුල විහාරස්ථානයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
25 | JAELA | 13 | DCB | 18 | 122 | 10 | 2019 |  | ජා ඇල දකුණු බටගම ශ්‍රී වජිරාරාමයේ සංවර්ධන කටයුතු සිදු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
26 | JAELA | 13 | DCB | 18 | 122 | 11 | 2019 |  | ජා ඇල නාරංගොඩපාළුව ශාසනෝදයාරාමයේ සංවර්ධන කටයුතු සිදු කිරීම. |  |  | Construction |  | 100000 | [5 empty] | 1
27 | JAELA | 13 | DCB | 18 | 122 | 12 | 2019 |  | ජා ඇල වල්පොල විමලරත්නාරාම පුරාණ විහාරස්ථානයේ සංවර්ධන කටයුතු කිරීම. |  |  | Construction |  | 50000 | [5 empty] | 1
28 | JAELA | 13 | DCB | 18 | 142 | 7 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ අඩු ආදායම්ලාභී තරුණ තරුණියන් සඳහා සැහැල්ලු හා බර වාහන රියදුරු බලපත්‍ර ලබා දීම. |  |  | Training Programs |  | #REF! | [5 empty] | 1
29 | JAELA | 13 | DCB | 18 | 142 | 8 | 2019 |  | ජා ඇල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ කාන්තාවන් සඳහා ස්වයං රැකියා පුහුණුව ලබා දීම. |  |  | Training Programs |  | #REF! | [5 empty] | 1
30 | JAELA | 14 | DCB | 18 | 151 | 1 | 2019 |  | රාගම තේවත්ත පාර සොයිසා නිවාස අවමංගල්‍යාධාර හා සුභසාධක සමිති ගොඩනැගිල්ලේ ඉතිරි වැඩ කටයුතු නිම කිරීම. |  |  | Construction |  | #REF! | [5 empty] | 1
31 | JAELA | 6 | DCB | 18 | 154 | 1 | 2019 |  | 183 නාගොඩ පාතිමා මාවතේ පොතුහැර ළිඳ සංවර්ධනය කිරීම සඳහා |  |  | Construction |  | #REF! | [5 empty] | 1
32 | JAELA | 6 | DCB | 18 | 124 | 1 | 2019 |  | 211 උතුරු බටගම ශ්‍රී සුමන විහාරස්ථානයේ දහම් පාසල් ගොඩනැගිල්ලේ වැඩ ආරම්භ කිරීම සඳහා |  |  | Construction |  | #REF! | [5 empty] | 1
33 | JAELA | 6 | DCB | 18 | 124 | 2 | 2019 |  | රාගම වල්පොල ශ්‍රී විමලරත්නාරාමයේ ගුණානන්ද දහම් පාසල් ගොඩනැගිල්ලේ ඉතිරි වැඩ කටයුතු සඳහා |  |  | Construction |  | #REF! | [5 empty] | 1
34 | JAELA | 7 | DCB | 18 | 152 | 12 | 2019 |  | ලිය සවිය කාන්තා කාර්යය සංවිධානය හා සුභ සාධක සමිතිය වෙත 10 × 20 තහඩු හට් 1 ක් හා ඇදි සහිත ප්ලාස්ටික් පුටු ලබා දීම. |  |  | Goods & Services) |  | #REF! | [5 empty] | 1
35 | JAELA | 7 | DCB | 18 | 152 | 13 | 2019 |  | ඒකල ශාන්ත මැතිව්ස් දේවස්ථානය වෙත ඇදි රහිත ප්ලාස්ටික් පුටු ලබා දීම. |  |  | Goods & Services) |  | #REF! | [5 empty] | 1
36 | JAELA | 7 | DCB | 18 | 152 | 14 | 2019 |  | කෘස්වත්ත නිර්මල දේවමාතා දේවස්ථානය වෙත 10 × 20 තහඩු හට් 1ක් හා ඇදි සහිත ප්ලාස්ටික් පුටු ලබා දීම. |  |  | Goods & Services) |  | #REF! | [5 empty] | 1
37 | JAELA | 7 | DCB | 18 | 152 | 15 | 2019 |  | දකුණු නිවන්දම අවමංගල්‍යාධාර සහනාධාර සමිතිය වෙත 10 × 20 තහඩු හට් 1 ක් හා ඇඳි සහිත ප්ලාස්ටික් පුටු ලබා දීම. |  |  | Goods & Services) |  | #REF! | [5 empty] | 1
38 | JAELA | 7 | DCB | 18 | 152 | 16 | 2019 |  | හෙරිටේජ් පාර්ක් සුබ සාධක සමිතිය 10 × 20 කැනපි හට් 1ක් සහ ඉතිරි මුදල් සඳහා ඇඳි සහිත ප්ලාස්ට්ක් පුටු ලබා දීම. |  |  | Goods & Services) |  | #REF! | [5 empty] | 1
39 | JAELA | 3 | DCB | 18 | 141 | 1 | 2019 |  | විසිතුරු මල් වගාකරන ස්වයං රැකියාලාභීන් පස් දෙනෙකු හට හට් ලබා දීම. |  |  | Goods & Services) |  | #REF! | [5 empty] | 1
40 | JAELA | 13 | DCB | 18 | 518 | 1 | 2019 |  | පොල්ගස්හේන ජේසු බිළිඳු පෙරපාසලේ උද්‍යාන සංවර්ධනය කිරීම. |  |  | Construction |  | #REF! | [5 empty] | 1
41 | JAELA | 13 | DCB | 18 | 515 | 2 | 2019 |  | ජා ඇල කොට්ඨාසයේ පෙර පාසල්වල සංවර්ධන කටයුතු කිරීම |  |  | Construction |  | #REF! | [5 empty] | 1
Total | [13 empty] | #REF! | #REF! |  |  |  |  | 35 |  | 3 | [6 empty] | 3
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos.
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos.
(c ) - Instructions to fill the Physical Progress
Description for rating
Estimate is being / to be prepared and initial works started
Constructions:
B - 1 = Estimates approved / Bid documents prepared,
B - 2 = Quotation / Bid called
B - 3 = Quotation / Bid Received
B - 4 = Contract Awarded. (25% completed)
Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared
Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments
Constructions : 60% Completed Other : Received goods / instruments as per the order
Constructions : 80% Completed Other : Received goods / instruments as per the order
Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries
Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs

## නගර සභා (hidden)
Decentralized Capital Budget Programme - 2019 - Gampaha District
Physical and Financial Progress of the 2019.06.22
Divisional Secretariat Division (a) | [8 empty] | Name: Ja Ela | [16 empty] | Annexure/DCB/02
[9 empty] | No: | [16 empty] | Detail Progress
SN | Project No | [6 empty] | Name of MP | Name of Project | G.N. Division (b) |  | Type of Project (Construction / Goods & Services) | Sector | Allocation - Value of the Project (Rs.) | Total Estimate Cost (Rs.) |  | Contract Amount (Rs) | Total Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
[20 empty] | A | B |  |  |  | C | D | E | F | G
| Division | MP No | Programme | Authority | Sector | No | Year |  |  | Name | No |  |  |  | With VAT | Without VAT |  |  |  |  | B -1 | B -2 | B-3 | B-4
[20 empty] | 0-5% | Estimate Approved & Bid Document Prepared | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 40-60% | 61-80% | 81-99% | 100%
1 | JAELA | 13 | DCB | 34 | 82 | 1 | 2019 |  | ජා ඇල දෑල ශාන්ත මරියා පාසල ඉදිරිපිට පාර ගල් අතුරා තාර දැමීම. |  |  |  |  | 250000 | [5 empty] | 1
2 | JAELA | 13 | DCB | 34 | 171 | 1 | 2019 |  | ජා ඇල 19/A ග්‍රාම නිලධාරී වසමේ දුම්රිය බඩු ගබඩා පාරේ පිහිටි වොලිබෝල් ක්‍රීඩා පිටිය සංවර්ධනය කිරීම. |  |  |  |  | 100000 | [5 empty] | 1
Total | [13 empty] | 350000 |  | 0 |  |  |  | 2
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos.
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos.
(c ) - Instructions to fill the Physical Progress
Description for rating
Estimate is being / to be prepared and initial works started
Constructions:
B - 1 = Estimates approved / Bid documents prepared,
B - 2 = Quotation / Bid called
B - 3 = Quotation / Bid Received
B - 4 = Contract Awarded. (25% completed)
Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared
Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments
Constructions : 60% Completed Other : Received goods / instruments as per the order
Constructions : 80% Completed Other : Received goods / instruments as per the order
Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries
Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs

## ප්‍රා.ස (hidden)
Decentralized Capital Budget Programme - 2019 - Gampaha District
Physical and Financial Progress - 2019.06.22
Divisional Secretariat Division (a) | [8 empty] | Name: Ja Ela | [11 empty] | Annexure/DCB/02
[9 empty] | No: | [11 empty] | Detail Progress
SN | Project No | [6 empty] | Name of MP | Name of Project | G.N. Division (b) |  | Type of Project (Construction / Goods & Services) | Allocation - Value of the Project (Rs.) | Total Estimate Cost (Rs.) | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
[15 empty] | A | B |  |  |  | C | D | E | F | G
| Division | MP No | Programme | Authority | Sector | No | Year |  |  | Name | No |  |  | With VAT |  | B -1 | B -2 | B-3 | B-4
[15 empty] | 0-5% | Estimate Approved & Bid Document Prepared | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 40-60% | 61-80% | 81-99% | 100%
1 | JAELA | 18 | DCB | 35 | 81 | 1 | 2019 |  | රාගම වැව ළග,ගනේ පාර සුරුවම ළග පිහිටි අතුරු පාර (පැටීමා ප්‍රනාන්දු නිවස) කොන්ක්‍රීට් කිරීම. |  |  |  | 200000 | 200000 | 1 |  | 1
2 | JAELA | 13 | DCB | 35 | 81 | 3 | 2019 |  | මහවත්ත පැතුම් පියස 02 වන පටුමග මාවත කොන්ක්‍රීට් කිරීම. |  |  |  | 250000 |  | 1
3 | JAELA | 13 | DCB | 35 | 81 | 4 | 2019 |  | ජා ඇල මා එළිය ශාන්ත රීටා මාවතේ 1056 මාවත කොන්ක්‍රීට් කිරීම. |  |  |  | 250000 |  | 1
4 | JAELA | 13 | DCB | 35 | 81 | 5 | 2019 |  | ජා ඇල පොල්ගහහේන මාර්ගයේ පීටර් පෙරේරා මාවතේ පළමු අතුරු මාර්ගය කොන්ක්‍රීට් කිරීම. |  |  |  | 250000 |  | 1
5 | JAELA | 13 | DCB | 35 | 81 | 6 | 2019 |  | නිවන්දම සීක්කුවත්ත නිවාස යෝජනා ක්‍රමයේ වටරවුම් පාර ප්‍රධාන මාර්ගය කොන්ක්‍රීට් කිරීම. |  |  |  | 250000 |  | 1
6 | JAELA | 13 | DCB | 35 | 171 | 7 | 2019 |  | පොල්ගහහේන වාසනා ක්‍රීඩාංගනය සංවර්ධනය කිරීම. |  |  |  | 250000 |  | 1
7 | JAELA | 13 | DCB | 35 | 131 | 8 | 2019 |  | ජා ඇල ජයශ්‍රීගම බහුකාර්යය සේවා පියසේ ඉතිරි සංවර්ධන කටයුතු කිරීම. |  |  |  | 150000 |  | 1
8 | JAELA | 13 | DCB | 35 | 81 | 9 | 2019 |  | තුඩැල්ල සුදුවැල්ල කතෝලික සුසාන භූමියට පිවිසෙන මාර්ගය කොන්ක්‍රීට් කිරීම. |  |  |  | 200000 |  | 1
9 | JAELA | 7 | DCB | 35 | 81 | 10 | 2019 |  | ජා ඇල ඉඳිමින්න ශාන්ත අන්තෝනි මුණිදුන්ගේ සුරුවම අසළින් ලලිත් කුමාර මහතාගේ නිවස අසළ පාර කොන්ක්‍රීට් කිරීම . |  |  |  | 250000 |  | 1
10 | JAELA | 7 | DCB | 35 | 81 | 11 | 2019 |  | රාගම තේවත්ත ලුරුදු මාවතේ දුමින්ද සිල්වා මහතාගේ නිවස අසළ මාවත කොන්ක්‍රීට් කිරීම . |  |  |  | 250000 |  | 1
Total | [12 empty] | 2300000 |  | 9 |  | 1
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos.
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos.
(c ) - Instructions to fill the Physical Progress
Description for rating
Estimate is being / to be prepared and initial works started
Constructions:
B - 1 = Estimates approved / Bid documents prepared,
B - 2 = Quotation / Bid called
B - 3 = Quotation / Bid Received
B - 4 = Contract Awarded. (25% completed)
Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared
Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments
Constructions : 60% Completed Other : Received goods / instruments as per the order
Constructions : 80% Completed Other : Received goods / instruments as per the order
Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries
Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs

## කලාප අධ්‍යාපන (hidden)
Decentralized Capital Budget Programme - 2019 - Gampaha District
Physical and Financial Progress of the 2019.06.22
Divisional Secretariat Division (a) | [8 empty] | Name: Ja Ela | [16 empty] | Annexure/DCB/02
[9 empty] | No: | [16 empty] | Detail Progress
SN | Project No | [6 empty] | Name of MP | Name of Project | G.N. Division (b) |  | Type of Project (Construction / Goods & Services) | Sector | Allocation - Value of the Project (Rs.) | Total Estimate Cost (Rs.) |  | Contract Amount (Rs) | Total Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
[20 empty] | A | B |  |  |  | C | D | E | F | G
| Division | MP No | Programme | Authority | Sector | No | Year |  |  | Name | No |  |  |  | With VAT | Without VAT |  |  |  |  | B -1 | B -2 | B-3 | B-4
[20 empty] | 0-5% | Estimate Approved & Bid Document Prepared | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 40-60% | 61-80% | 81-99% | 100%
1 | JAELA | 7 | DCB | 44 | 53 | 1 | 2019 |  | තුඩැල්ල නිමලමරියා බාලිකා විද්‍යාලයේ නව ගණිතාගාරය සඳහා සුහුරු පුවරුවක් (interactive white board) ලබා දීම. |  |  |  |  | #REF! | [5 empty] | 1
Total | [13 empty] | #REF! |  | 0 |  |  |  | 1
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos.
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos.
(c ) - Instructions to fill the Physical Progress
Description for rating
Estimate is being / to be prepared and initial works started
Constructions:
B - 1 = Estimates approved / Bid documents prepared,
B - 2 = Quotation / Bid called
B - 3 = Quotation / Bid Received
B - 4 = Contract Awarded. (25% completed)
Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared
Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments
Constructions : 60% Completed Other : Received goods / instruments as per the order
Constructions : 80% Completed Other : Received goods / instruments as per the order
Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries
Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs

## ප්‍රාදේශීය ඉංජිනේරු (hidden)
Decentralized Capital Budget Programme - 2019 - Gampaha District
Physical and Financial Progress of the 2019.06.22
Divisional Secretariat Division (a) | [8 empty] | Name: Ja Ela | [16 empty] | Annexure/DCB/02
[9 empty] | No: | [16 empty] | Detail Progress
SN | Project No | [6 empty] | Name of MP | Name of Project | G.N. Division (b) |  | Type of Project (Construction / Goods & Services) | Sector | Allocation - Value of the Project (Rs.) | Total Estimate Cost (Rs.) |  | Contract Amount (Rs) | Total Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
[20 empty] | A | B |  |  |  | C | D | E | F | G
| Division | MP No | Programme | Authority | Sector | No | Year |  |  | Name | No |  |  |  | With VAT | Without VAT |  |  |  |  | B -1 | B -2 | B-3 | B-4
[20 empty] | 0-5% | Estimate Approved & Bid Document Prepared | Quotation / Bid Called | Quotation / Bid Received | Contract Awarded | 26-40% | 40-60% | 61-80% | 81-99% | 100%
1 | JAELA | 13 | DCB | 50 | 171 | 1 | 2019 |  | පේරලන්ද කනිෂ්ඨ ද්වීතීක විද්‍යාලයේ ක්‍රීඩාපිටියේ ඉතිරි කොටස සංවර්ධනය කිරීම. |  |  |  |  | #REF! | [5 empty] | 1
Total | [13 empty] | #REF! |  | 0 |  |  |  | 1
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos.
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos.
(c ) - Instructions to fill the Physical Progress
Description for rating
Estimate is being / to be prepared and initial works started
Constructions:
B - 1 = Estimates approved / Bid documents prepared,
B - 2 = Quotation / Bid called
B - 3 = Quotation / Bid Received
B - 4 = Contract Awarded. (25% completed)
Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared
Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments
Constructions : 60% Completed Other : Received goods / instruments as per the order
Constructions : 80% Completed Other : Received goods / instruments as per the order
Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries
Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs